## in
No | Activity | Description | Team | Risk Level | BackEnd man/day | DBA man/day | FrontEnd man/day | DevOps man/day | BE O | DBA O | FE O | DEVOPS O | BE ML | DBA ML | FE ML | DEVOPS ML | BE P | DBA P | FE P | DEVOPS P | BE ES | DBA ES | FE ES | DEVOPS ES
[9 empty] | Optimistic | 1 | 1 | 1 | Most likely | 1.2 | 1.5 | 2 | Pessimistic | 2 | 2.5 | 3 | PERT Estimation
1 | Transactions Service
| API Controllers | Handle HTTP requests from SPA portals and route them to application layer. | Dev backend | Low | 10 |  |  | 10 | 10 |  |  | 10 | 12 | 0 | 0 | 12 | 20 | 0 | 0 | 20
| Command Handlers | Process commands that represent user intentions to change system state. | Dev backend | Medium | 12 |  |  |  | 8 |  |  |  | 12 | 0 | 0 | 0 | 20 | 0 | 0 | 0
| Event Handlers | React to internal or external events, including those from Cosmos DB change feed. | Dev backend | Medium | 12 |  |  |  | 8 |  |  |  | 12 | 0 | 0 | 0 | 20 | 0 | 0 | 0
| Business Logic Implementation | Implements domain rules and workflows like booking flow or transport combining. | Dev backend | High | 24 |  |  |  | 12 |  |  |  | 24 | 0 | 0 | 0 | 36 | 0 | 0 | 0
| Database Repository | Handles data persistence and retrieval from DB. | Dev backend | Medium | 9 | 15 |  | 1 | 6 | 15 |  | 1 | 9 | 22.5 | 0 | 1.5 | 15 | 37.5 | 0 | 2.5
| Event Store Repository | Stores domain events in an append-only fashion for auditing and replay. | Dev backend | Medium | 7.5 | 10 |  |  | 5 | 10 |  |  | 7.5 | 15 | 0 | 0 | 12.5 | 25 | 0 | 0
| Cosmos DB Change Feed Listener | Listens to Cosmos DB changes and triggers event handlers. | Dev backend | Medium | 7.5 |  |  | 1 | 5 |  |  | 1 | 7.5 | 0 | 0 | 1.5 | 12.5 | 0 | 0 | 2.5
| External Service Integrations | Handles calls to external services like Uber, CTC, UPSA. | Dev backend | High | 20 |  |  |  | 10 |  |  |  | 20 | 0 | 0 | 0 | 30 | 0 | 0 | 0
| Validation Layer | Performs input and business rule validations. | Dev backend | Low | 4 |  |  |  | 4 |  |  |  | 4.8 | 0 | 0 | 0 | 8 | 0 | 0 | 0
| Authentication & Authorization | Secures APIs via JWT, Azure AD, etc. | Dev backend | Low | 4 |  |  | 3 | 4 |  |  | 3 | 4.8 | 0 | 0 | 3.6 | 8 | 0 | 0 | 6
| Logging & Telemetry | Logs important actions and errors, provides observability via App Insights. | Dev backend | Low | 4 |  |  | 5 | 4 |  |  | 5 | 4.8 | 0 | 0 | 6 | 8 | 0 | 0 | 10
| Configuration Management | Uses Azure App Configuration or similar to manage feature flags and app settings. | DevOps | Low | 3 |  |  | 3 | 3 |  |  | 3 | 3.6 | 0 | 0 | 3.6 | 6 | 0 | 0 | 6
| Caching Layer | Optional caching for frequent read data using Redis or in-memory caches. | Dev backend | Low | 3 |  |  | 1 | 3 |  |  | 1 | 3.6 | 0 | 0 | 1.2 | 6 | 0 | 0 | 2
| Saga/Orchestration Engine | Optional long-running transaction coordinator using Durable Functions. | Dev backend | High | 14 |  |  |  | 7 |  |  |  | 14 | 0 | 0 | 0 | 21 | 0 | 0 | 0
| API Gateway / BFF | Optional API facade between frontend and microservices. | Dev backend, Dev front End | Medium | 9 |  | 3 |  | 6 |  | 3 |  | 9 | 0 | 4.5 | 0 | 15 | 0 | 7.5 | 0
| Unit Tests |  | Dev backend | Medium | 15 |  |  |  | 10 |  |  |  | 15 | 0 | 0 | 0 | 25 | 0 | 0 | 0
| Integration Tests |  | Dev backend | High | 16 |  |  |  | 8 |  |  |  | 16 | 0 | 0 | 0 | 24 | 0 | 0 | 0
| Total |  |  |  | 174 | 25 | 3 | 24 | 113 | 25 | 3 | 24 | 179.6 | 37.5 | 4.5 | 29.4 | 287 | 62.5 | 7.5 | 49 | 186.4 | 39.5833 | 4.75 | 31.7667
2 | Booking Service
| API Controllers | Expose REST endpoints for booking-related operations like create, update, cancel. | Dev backend | Low | 10 |  |  | 10 | 10 |  |  | 10 | 12 | 0 | 0 | 12 | 20 | 0 | 0 | 20
| Command Handlers | Process booking commands such as CreateBooking, CancelBooking. | Dev backend | Medium | 12 |  |  |  | 8 |  |  |  | 12 | 0 | 0 | 0 | 20 | 0 | 0 | 0
| Event Handlers | Handle events related to booking lifecycle like BookingConfirmed, BookingCancelled. | Dev backend | Medium | 12 |  |  |  | 8 |  |  |  | 12 | 0 | 0 | 0 | 20 | 0 | 0 | 0
| Booking Logic | Implements core business logic such as prioritization, approval workflow. | Dev backend | High | 24 |  |  |  | 12 |  |  |  | 24 | 0 | 0 | 0 | 36 | 0 | 0 | 0
| Booking Repository | Persists booking data, including state transitions, in Cosmos DB. | Dev backend | Medium | 9 | 10 |  |  | 6 | 10 |  |  | 9 | 15 | 0 | 0 | 15 | 25 | 0 | 0
| Validation Engine | Validates booking rules, inputs and user permissions. | Dev backend | Low | 4 |  |  |  | 4 |  |  |  | 4.8 | 0 | 0 | 0 | 8 | 0 | 0 | 0
| Notification Service Integration | Sends booking status updates via email or SMS. | Dev backend | Medium | 7.5 |  |  |  | 5 |  |  |  | 7.5 | 0 | 0 | 0 | 12.5 | 0 | 0 | 0
| Policy Evaluation Client | Calls Policy Service to evaluate booking eligibility and prioritization. | Dev backend | Medium | 9 |  |  |  | 6 |  |  |  | 9 | 0 | 0 | 0 | 15 | 0 | 0 | 0
| Booking Event Publisher | Publishes domain events to Event Bus or Event Store. | Dev backend | Medium | 7.5 |  |  |  | 5 |  |  |  | 7.5 | 0 | 0 | 0 | 12.5 | 0 | 0 | 0
| Cosmos DB Change Feed Processor | Listens to changes in booking documents to trigger downstream processing. | Dev backend | Medium | 7.5 |  |  | 1 | 5 |  |  | 1 | 7.5 | 0 | 0 | 1.5 | 12.5 | 0 | 0 | 2.5
| Audit Logging | Logs booking-related operations for traceability. | DevOps, Dev backend | Low | 3 |  |  | 3 | 3 |  |  | 3 | 3.6 | 0 | 0 | 3.6 | 6 | 0 | 0 | 6
| External Supplier Connector | Optional integration with third-party hotel or transport suppliers. | Dev backend | High | 14 |  |  |  | 7 |  |  |  | 14 | 0 | 0 | 0 | 21 | 0 | 0 | 0
| Report Trigger Engine | Optional component to trigger reporting based on booking actions. | Dev backend | Low | 4 |  |  |  | 4 |  |  |  | 4.8 | 0 | 0 | 0 | 8 | 0 | 0 | 0
| Feature Flag Manager | Manages conditional logic or experiments using feature flags. | DevOps | Low | 3 |  |  |  | 3 |  |  |  | 3.6 | 0 | 0 | 0 | 6 | 0 | 0 | 0
| Unit Tests |  | Dev backend | Medium | 15 |  |  |  | 10 |  |  |  | 15 | 0 | 0 | 0 | 25 | 0 | 0 | 0
| Integration Tests |  | Dev backend | High | 16 |  |  |  | 8 |  |  |  | 16 | 0 | 0 | 0 | 24 | 0 | 0 | 0
| Total |  |  |  | 157.5 | 10 | 0 | 14 | 104 | 10 | 0 | 14 | 162.3 | 15 | 0 | 17.1 | 261.5 | 25 | 0 | 28.5 | 169.1167 | 15.8333 | 0 | 18.4833
3 | Policies Configuration Service
| API Controllers | Expose endpoints to create, update, and fetch policy configurations. | Dev backend | Low | 10 |  |  | 10 | 10 |  |  | 10 | 12 | 0 | 0 | 12 | 20 | 0 | 0 | 20
| Policy Rule Editor | Enables creation and modification of booking/prioritization rules. | Dev backend | Medium | 9 |  |  |  | 6 |  |  |  | 9 | 0 | 0 | 0 | 15 | 0 | 0 | 0
| Validation Engine | Validates business logic, conflicts, and rule integrity. | Dev backend | Medium | 7.5 |  |  |  | 5 |  |  |  | 7.5 | 0 | 0 | 0 | 12.5 | 0 | 0 | 0
| Policy Repository | Stores policy configurations and version history. | Dev backend, DBA | Low | 5 | 10 |  | 3 | 5 | 10 |  | 3 | 6 | 12 | 0 | 3.6 | 10 | 20 | 0 | 6
| Policy Evaluator | Evaluates policies at runtime when queried by other services. | Dev backend | Medium | 9 |  |  |  | 6 |  |  |  | 9 | 0 | 0 | 0 | 15 | 0 | 0 | 0
| Versioning Engine | Tracks and manages versions of rules and configurations. | Dev backend | Low | 4 |  |  |  | 4 |  |  |  | 4.8 | 0 | 0 | 0 | 8 | 0 | 0 | 0
| Access Control Logic | Ensures only authorized users can modify/view policies. | Dev backend | Low | 3 |  |  |  | 3 |  |  |  | 3.6 | 0 | 0 | 0 | 6 | 0 | 0 | 0
| Change Notification Publisher | Sends events or notifications when policies are updated. | Dev backend | Low | 4 |  |  |  | 4 |  |  |  | 4.8 | 0 | 0 | 0 | 8 | 0 | 0 | 0
| Configuration API Client | Optional client for integration with Azure App Configuration or Feature Management. | DevOps | Low | 3 |  |  | 1 | 3 |  |  | 1 | 3.6 | 0 | 0 | 1.2 | 6 | 0 | 0 | 2
| Audit Logger | Logs all changes and accesses to policy rules for compliance. | DevOps, Dev backend | Low | 3 |  |  | 1 | 3 |  |  | 1 | 3.6 | 0 | 0 | 1.2 | 6 | 0 | 0 | 2
| Unit Tests |  | Dev backend | Low | 7 |  |  |  | 7 |  |  |  | 8.4 | 0 | 0 | 0 | 14 | 0 | 0 | 0
| Integration Tests |  | Dev backend | Medium | 9 |  |  |  | 6 |  |  |  | 9 | 0 | 0 | 0 | 15 | 0 | 0 | 0
| Total |  |  |  | 73.5 | 10 | 0 | 15 | 62 | 10 | 0 | 15 | 81.3 | 12 | 0 | 18 | 135.5 | 20 | 0 | 30 | 87.1167 | 13 | 0 | 19.5
4 | SPA applications
| Supplier Dashboard | Provides suppliers with access to upload and manage booking and pricing data. | Dev front End | Medium |  |  | 0 | 10 |  |  | 22.5 | 10 | 0 | 0 | 33.75 | 15 | 0 | 0 | 56.25 | 25
| Booking Upload View | Allows manual upload of available hotel/transport bookings. | Dev front End | Low |  |  | 0 |  |  |  | 10 |  | 0 | 0 | 12 | 0 | 0 | 0 | 20 | 0
| Pricing Configuration View | Interface for entering and updating pricing details. | Dev front End | Low |  |  | 0 |  |  |  | 10 |  | 0 | 0 | 12 | 0 | 0 | 0 | 20 | 0
| Notification Center | Displays notifications from the system for updates or actions. | Dev front End | Low |  |  | 0 |  |  |  | 10 |  | 0 | 0 | 12 | 0 | 0 | 0 | 20 | 0
| Booking Management View | Manage hotel/transport bookings, statuses, and approvals. | Dev front End | Medium |  |  | 0 |  |  |  | 22.5 |  | 0 | 0 | 33.75 | 0 | 0 | 0 | 56.25 | 0
| Supplier Configuration View | Manage suppliers and booking rules. | Dev front End | Medium |  |  | 0 |  |  |  | 15 |  | 0 | 0 | 22.5 | 0 | 0 | 0 | 37.5 | 0
| Policy Management View | Configure and manage booking policies and prioritization rules. | Dev front End | Medium |  |  | 0 |  |  |  | 15 |  | 0 | 0 | 22.5 | 0 | 0 | 0 | 37.5 | 0
| Reports View | Access and download reports related to bookings and finances. | Dev front End | Low |  |  | 0 |  |  |  | 8 |  | 0 | 0 | 9.6 | 0 | 0 | 0 | 16 | 0
| User Access Management | Manage roles, access levels, and users for portals and systems. | Dev front End | Low |  |  | 0 |  |  |  | 10 |  | 0 | 0 | 12 | 0 | 0 | 0 | 20 | 0
| System Monitoring Dashboard | Monitor application health, logs, and services. | Dev front End | Medium |  |  | 0 |  |  |  | 12 |  | 0 | 0 | 18 | 0 | 0 | 0 | 30 | 0
| Configuration Console | Access feature flags, environment settings, etc. | Dev front End | Low |  |  | 0 |  |  |  | 8 |  | 0 | 0 | 9.6 | 0 | 0 | 0 | 16 | 0
| My Bookings View | View and confirm hotel/transport bookings. | Dev front End | Low |  |  | 0 |  |  |  | 10 |  | 0 | 0 | 12 | 0 | 0 | 0 | 20 | 0
| Feedback Form | Submit feedback on bookings or travel experience. | Dev front End | Low |  |  | 0 |  |  |  | 5 |  | 0 | 0 | 6 | 0 | 0 | 0 | 10 | 0
| Reservation Print View | Display printable view of confirmed reservations. | Dev front End | Low |  |  | 0 |  |  |  | 5 |  | 0 | 0 | 6 | 0 | 0 | 0 | 10 | 0
| SSO Integration | Enable seamless login via company SSO. | Dev front End | Low |  |  | 0 |  |  |  | 2 |  | 0 | 0 | 2.4 | 0 | 0 | 0 | 4 | 0
| Unit Tests |  | Dev backend | Medium |  |  | 0 |  |  |  | 15 |  | 0 | 0 | 22.5 | 0 | 0 | 0 | 37.5 | 0
| Integration Tests |  | Dev backend | High |  |  | 0 |  |  |  | 30 |  | 0 | 0 | 60 | 0 | 0 | 0 | 90 | 0
| Total |  |  |  | 0 | 0 | 0 | 10 | 0 | 0 | 210 | 10 | 0 | 0 | 306.6 | 15 | 0 | 0 | 501 | 25 | 0 | 0 | 322.9 | 15.8333
5 | Hotel Service
| API Controllers | Expose endpoints to manage hotel availability, booking, and pricing. | Dev backend | Low | 10 |  |  | 10 | 10 |  |  | 10 | 12 | 0 | 0 | 12 | 20 | 0 | 0 | 20
| Hotel Command Handlers | Handle commands for managing hotel listings and bookings. | Dev backend | Medium | 9 |  |  |  | 6 |  |  |  | 9 | 0 | 0 | 0 | 15 | 0 | 0 | 0
| Event Handlers | Respond to booking-related events to reserve or release hotel rooms. | Dev backend | Medium | 9 |  |  |  | 6 |  |  |  | 9 | 0 | 0 | 0 | 15 | 0 | 0 | 0
| Hotel Logic | Implements hotel-specific logic including room selection, rules, etc. | Dev backend | High | 16 |  |  |  | 8 |  |  |  | 16 | 0 | 0 | 0 | 24 | 0 | 0 | 0
| Hotel Repository | Stores hotel information, availability, and booking data. | Dev backend, DBA | Medium | 9 | 10 |  |  | 6 | 10 |  |  | 9 | 15 | 0 | 0 | 15 | 25 | 0 | 0
| Supplier Integration Adapter | Integrates with third-party hotel suppliers or manual upload services. | Dev backend | High | 14 |  |  |  | 7 |  |  |  | 14 | 0 | 0 | 0 | 21 | 0 | 0 | 0
| Change Feed Listener | Watches for updates in hotel availability or bookings. | Dev backend | Medium | 6 |  |  |  | 4 |  |  |  | 6 | 0 | 0 | 0 | 10 | 0 | 0 | 0
| Availability Validator | Ensures requested bookings comply with availability rules. | Dev backend | Low | 4 |  |  |  | 4 |  |  |  | 4.8 | 0 | 0 | 0 | 8 | 0 | 0 | 0
| Pricing Engine | Calculates or validates pricing and discounts per rules. | Dev backend | Medium | 7.5 |  |  |  | 5 |  |  |  | 7.5 | 0 | 0 | 0 | 12.5 | 0 | 0 | 0
| Audit Logger | Logs key hotel service actions for traceability. | DevOps, Dev backend | Low | 3 |  |  | 3 | 3 |  |  | 3 | 3.6 | 0 | 0 | 3.6 | 6 | 0 | 0 | 6
| Notification Trigger | Triggers booking confirmation or failure notices. | Dev backend | Low | 4 |  |  |  | 4 |  |  |  | 4.8 | 0 | 0 | 0 | 8 | 0 | 0 | 0
| Unit Tests |  | Dev backend | Medium | 10.5 |  |  |  | 7 |  |  |  | 10.5 | 0 | 0 | 0 | 17.5 | 0 | 0 | 0
| Integration Tests |  | Dev backend | High | 12 |  |  |  | 6 |  |  |  | 12 | 0 | 0 | 0 | 18 | 0 | 0 | 0
| Total |  |  |  | 114 | 10 | 0 | 13 | 76 | 10 | 0 | 13 | 118.2 | 15 | 0 | 15.6 | 190 | 25 | 0 | 26 | 123.1333 | 15.8333 | 0 | 16.9
6 | Transport Service
| API Controllers | Expose endpoints to manage and retrieve transport bookings. | Dev backend | Low | 10 |  |  | 10 | 10 |  |  | 10 | 12 | 0 | 0 | 12 | 20 | 0 | 0 | 20
| Command Handlers | Handle commands related to transport booking creation or updates. | Dev backend | Medium | 9 |  |  |  | 6 |  |  |  | 9 | 0 | 0 | 0 | 15 | 0 | 0 | 0
| Event Handlers | React to events like transport booking requests or updates from other services. | Dev backend | Medium | 9 |  |  |  | 6 |  |  |  | 9 | 0 | 0 | 0 | 15 | 0 | 0 | 0
| Transport Logic | Implements transport booking workflows and validations. | Dev backend | High | 16 |  |  |  | 8 |  |  |  | 16 | 0 | 0 | 0 | 24 | 0 | 0 | 0
| Transport Repository | Stores transport booking data and trip history. | Dev backend, DBA | Medium | 7.5 | 10 |  |  | 5 | 10 |  |  | 7.5 | 15 | 0 | 0 | 12.5 | 25 | 0 | 0
| Location Management Module | Handles pick-up and drop-off locations including overrides. | Dev backend | Low | 4 |  |  |  | 4 |  |  |  | 4.8 | 0 | 0 | 0 | 8 | 0 | 0 | 0
| Transport Combining Engine | Optional logic for combining multiple bookings to optimize routes. | Dev backend | High | 12 |  |  |  | 6 |  |  |  | 12 | 0 | 0 | 0 | 18 | 0 | 0 | 0
| External Supplier Connector | Integration module for Uber or other transport providers. | Dev backend | High | 14 |  |  |  | 7 |  |  |  | 14 | 0 | 0 | 0 | 21 | 0 | 0 | 0
| Cosmos DB Change Feed Listener | Listens to changes in transport data and triggers business logic. | Dev backend | Medium | 6 |  |  |  | 4 |  |  |  | 6 | 0 | 0 | 0 | 10 | 0 | 0 | 0
| Notification Integration | Triggers notifications on transport booking status changes. | Dev backend | Low | 3 |  |  |  | 3 |  |  |  | 3.6 | 0 | 0 | 0 | 6 | 0 | 0 | 0
| Audit Logger | Logs transport-related transactions and actions. | DevOps, Dev backend | Low | 3 |  |  | 1 | 3 |  |  | 1 | 3.6 | 0 | 0 | 1.2 | 6 | 0 | 0 | 2
| Unit Tests |  | Dev backend | Medium | 12 |  |  |  | 8 |  |  |  | 12 | 0 | 0 | 0 | 20 | 0 | 0 | 0
| Integration Tests |  | Dev backend | High | 14 |  |  |  | 7 |  |  |  | 14 | 0 | 0 | 0 | 21 | 0 | 0 | 0
| Total |  |  |  | 119.5 | 10 | 0 | 11 | 77 | 10 | 0 | 11 | 123.5 | 15 | 0 | 13.2 | 196.5 | 25 | 0 | 22 | 127.9167 | 15.8333 | 0 | 14.3
7 | Hotel&Transport Suppliers Service
| API Controllers | Expose endpoints for suppliers to upload and manage availability and pricing. | Dev backend | Low | 10 |  |  | 10 | 10 |  |  | 10 | 12 | 0 | 0 | 12 | 20 | 0 | 0 | 20
| Supplier Upload Handler | Processes manual or batch uploads from hotel and transport suppliers. | Dev backend | Medium | 9 |  |  |  | 6 |  |  |  | 9 | 0 | 0 | 0 | 15 | 0 | 0 | 0
| Availability Repository | Stores hotel room and transport slot availability data. | Dev backend, DBA | Medium | 7.5 | 10 |  |  | 5 | 10 |  |  | 7.5 | 15 | 0 | 0 | 12.5 | 25 | 0 | 0
| Pricing Repository | Stores pricing data provided by suppliers. | Dev backend, DBA | Medium | 7.5 | 10 |  |  | 5 | 10 |  |  | 7.5 | 15 | 0 | 0 | 12.5 | 25 | 0 | 0
| Validation Engine | Validates uploaded supplier data against format and business rules. | Dev backend | Low | 4 |  |  |  | 4 |  |  |  | 4.8 | 0 | 0 | 0 | 8 | 0 | 0 | 0
| Manual Booking Support Module | Supports manual booking flows managed by travel managers. | Dev backend | Medium | 9 |  |  |  | 6 |  |  |  | 9 | 0 | 0 | 0 | 15 | 0 | 0 | 0
| Supplier Access Management | Manages authentication and authorization for suppliers. | Dev backend | Low | 3 |  |  |  | 3 |  |  |  | 3.6 | 0 | 0 | 0 | 6 | 0 | 0 | 0
| Change Notification Publisher | Notifies internal services when supplier data changes. | Dev backend | Low | 4 |  |  |  | 4 |  |  |  | 4.8 | 0 | 0 | 0 | 8 | 0 | 0 | 0
| Audit Logger | Logs supplier uploads, changes, and accesses. | DevOps, Dev backend | Low | 3 |  |  | 1 | 3 |  |  | 1 | 3.6 | 0 | 0 | 1.2 | 6 | 0 | 0 | 2
| Monitoring & Alerting | Tracks upload errors, performance, and system health. | DevOps | Low | 3 |  |  | 3 | 3 |  |  | 3 | 3.6 | 0 | 0 | 3.6 | 6 | 0 | 0 | 6
| Unit Tests |  | Dev backend | Medium | 10.5 |  |  |  | 7 |  |  |  | 10.5 | 0 | 0 | 0 | 17.5 | 0 | 0 | 0
| Integration Tests |  | Dev backend | High | 12 |  |  |  | 6 |  |  |  | 12 | 0 | 0 | 0 | 18 | 0 | 0 | 0
| Total |  |  |  | 82.5 | 20 | 0 | 14 | 62 | 20 | 0 | 14 | 87.9 | 30 | 0 | 16.8 | 144.5 | 50 | 0 | 28 | 93.0167 | 31.6667 | 0 | 18.2
8 | Notifications Service
| API Controllers | Expose endpoints to trigger notifications from other services. | Dev backend | Low | 10 |  |  | 10 | 10 |  |  | 10 | 12 | 0 | 0 | 12 | 20 | 0 | 0 | 20
| Notification Dispatcher | Routes notification requests to appropriate channels (email, SMS, etc). | Dev backend | Medium | 9 |  |  |  | 6 |  |  |  | 9 | 0 | 0 | 0 | 15 | 0 | 0 | 0
| Template Engine | Handles message templating and personalization for different channels. | Dev backend | Medium | 7.5 |  |  |  | 5 |  |  |  | 7.5 | 0 | 0 | 0 | 12.5 | 0 | 0 | 0
| Channel Integrations | Integrates with providers like SendGrid, Twilio, or SMTP servers. | Dev backend | Medium | 9 |  |  |  | 6 |  |  |  | 9 | 0 | 0 | 0 | 15 | 0 | 0 | 0
| Notification Scheduler | Optional component to schedule notifications (e.g., reminders). | Dev backend | Low | 4 |  |  |  | 4 |  |  |  | 4.8 | 0 | 0 | 0 | 8 | 0 | 0 | 0
| Retry Handler | Handles transient delivery failures and retries. | Dev backend | Low | 3 |  |  |  | 3 |  |  |  | 3.6 | 0 | 0 | 0 | 6 | 0 | 0 | 0
| Notification Repository | Stores notification history and metadata. | Dev backend, DBA | Low | 4 | 10 |  |  | 4 | 10 |  |  | 4.8 | 12 | 0 | 0 | 8 | 20 | 0 | 0
| Monitoring & Alerting | Tracks delivery success/failure and raises alerts. | DevOps | Low | 3 |  |  | 1 | 3 |  |  | 1 | 3.6 | 0 | 0 | 1.2 | 6 | 0 | 0 | 2
| Security & Validation | Validates incoming requests and ensures secure messaging. | Dev backend | Low | 3 |  |  |  | 3 |  |  |  | 3.6 | 0 | 0 | 0 | 6 | 0 | 0 | 0
| Audit Logger | Logs all sent notifications for traceability and compliance. | DevOps, Dev backend | Low | 3 |  |  | 1 | 3 |  |  | 1 | 3.6 | 0 | 0 | 1.2 | 6 | 0 | 0 | 2
| Feature Toggle Manager | Controls enabling/disabling of notification types via config or flags. | DevOps | Low | 2 |  |  | 2 | 2 |  |  | 2 | 2.4 | 0 | 0 | 2.4 | 4 | 0 | 0 | 4
| Unit Tests |  | Dev backend | Low | 6 |  |  |  | 6 |  |  |  | 7.2 | 0 | 0 | 0 | 12 | 0 | 0 | 0
| Integration Tests |  | Dev backend | Medium | 9 |  |  |  | 6 |  |  |  | 9 | 0 | 0 | 0 | 15 | 0 | 0 | 0
| Total |  |  |  | 72.5 | 10 | 0 | 14 | 61 | 10 | 0 | 14 | 80.1 | 12 | 0 | 16.8 | 133.5 | 20 | 0 | 28 | 85.8167 | 13 | 0 | 18.2
9 | Reporting Service
| API Controllers | Expose REST endpoints to retrieve reports and metrics. | Dev backend | Low | 10 |  |  | 10 | 10 |  |  | 10 | 12 | 0 | 0 | 12 | 20 | 0 | 0 | 20
| Report Generator | Generates booking, financial, and supplier reports from data sources. | Dev backend | Medium | 15 |  |  |  | 10 |  |  |  | 15 | 0 | 0 | 0 | 25 | 0 | 0 | 0
| Query Handlers | Process report queries and orchestrate data fetch logic. | Dev backend | Medium | 9 |  |  |  | 6 |  |  |  | 9 | 0 | 0 | 0 | 15 | 0 | 0 | 0
| Data Aggregator | Aggregates and transforms raw booking and transaction data for reporting. | Dev backend | Medium | 10.5 | 10 |  |  | 7 | 10 |  |  | 10.5 | 15 | 0 | 0 | 17.5 | 25 | 0 | 0
| Scheduled Report Engine | Handles periodic generation and distribution of reports. | Dev backend | Medium | 7.5 |  |  | 3 | 5 |  |  | 3 | 7.5 | 0 | 0 | 4.5 | 12.5 | 0 | 0 | 7.5
| Export Module | Supports exporting reports to PDF, Excel, or CSV formats. | Dev backend | Low | 4 |  |  |  | 4 |  |  |  | 4.8 | 0 | 0 | 0 | 8 | 0 | 0 | 0
| Reporting Database | Optimized reporting database or data warehouse (read-only model). | DBA | Medium | 9 | 10 |  |  | 6 | 10 |  |  | 9 | 15 | 0 | 0 | 15 | 25 | 0 | 0
| Authentication & Authorization | Secures access to reporting endpoints and data. | Dev backend | Low | 3 |  |  |  | 3 |  |  |  | 3.6 | 0 | 0 | 0 | 6 | 0 | 0 | 0
| Audit Logger | Logs report access and generation events. | DevOps, Dev backend | Low | 3 |  |  |  | 3 |  |  |  | 3.6 | 0 | 0 | 0 | 6 | 0 | 0 | 0
| Monitoring & Alerts | Monitors report generation jobs and errors. | DevOps | Low | 3 |  |  |  | 3 |  |  |  | 3.6 | 0 | 0 | 0 | 6 | 0 | 0 | 0
| Visualization Integration | Optional integration with Power BI or other visualization tools. | Dev backend | Medium | 9 | 10 |  |  | 6 | 10 |  |  | 9 | 15 | 0 | 0 | 15 | 25 | 0 | 0
| Unit Tests |  | Dev backend | Low | 7 |  |  |  | 7 |  |  |  | 8.4 | 0 | 0 | 0 | 14 | 0 | 0 | 0
| Integration Tests |  | Dev backend | Medium | 9 |  |  |  | 6 |  |  |  | 9 | 0 | 0 | 0 | 15 | 0 | 0 | 0
| Total |  |  |  | 99 | 30 | 0 | 13 | 76 | 30 | 0 | 13 | 105 | 45 | 0 | 16.5 | 175 | 75 | 0 | 27.5 | 111.8333 | 47.5 | 0 | 17.75
10 | Reactor Service
| Event Listener | Consumes events from Event Store or Cosmos DB change feed. | Dev backend | Medium | 15 |  |  | 10 | 10 |  |  | 10 | 15 | 0 | 0 | 15 | 25 | 0 | 0 | 25
| Event Dispatcher | Routes incoming events to appropriate internal handlers. | Dev backend | Low | 4 |  |  |  | 4 |  |  |  | 4.8 | 0 | 0 | 0 | 8 | 0 | 0 | 0
| Reactor Logic | Executes domain reactions to events (e.g., update, notify, trigger workflows). | Dev backend | High | 20 |  |  |  | 10 |  |  |  | 20 | 0 | 0 | 0 | 30 | 0 | 0 | 0
| Event Handlers | Handle domain events and invoke corresponding services or commands. | Dev backend | Medium | 9 |  |  |  | 6 |  |  |  | 9 | 0 | 0 | 0 | 15 | 0 | 0 | 0
| Rule Evaluation Engine | Applies business rules to determine reactions or validations. | Dev backend | Medium | 9 |  |  |  | 6 |  |  |  | 9 | 0 | 0 | 0 | 15 | 0 | 0 | 0
| External Service Notifier | Sends notifications or follow-ups to external systems after event handling. | Dev backend | Medium | 7.5 |  |  |  | 5 |  |  |  | 7.5 | 0 | 0 | 0 | 12.5 | 0 | 0 | 0
| State Updater | Updates system state or projections based on handled events. | Dev backend, DBA | Medium | 7.5 |  | 5 |  | 5 |  | 5 |  | 7.5 | 0 | 7.5 | 0 | 12.5 | 0 | 12.5 | 0
| Audit Logger | Logs handled events and outcomes for auditing and tracing. | DevOps, Dev backend | Low | 3 |  |  | 5 | 3 |  |  | 5 | 3.6 | 0 | 0 | 6 | 6 | 0 | 0 | 10
| Retry and Dead Letter Processor | Handles transient failures and retries event handling or dead-lettering. | Dev backend | Medium | 6 |  |  |  | 4 |  |  |  | 6 | 0 | 0 | 0 | 10 | 0 | 0 | 0
| Monitoring & Alerting | Monitors event processing throughput and errors. | DevOps | Low | 3 |  |  | 3 | 3 |  |  | 3 | 3.6 | 0 | 0 | 3.6 | 6 | 0 | 0 | 6
| Feature Toggle Manager | Controls enabled reactions and flows via feature flags. | DevOps | Low | 2 |  |  | 2 | 2 |  |  | 2 | 2.4 | 0 | 0 | 2.4 | 4 | 0 | 0 | 4
| Unit Tests |  | Dev backend | Medium | 12 |  |  |  | 8 |  |  |  | 12 | 0 | 0 | 0 | 20 | 0 | 0 | 0
| Integration Tests |  | Dev backend | High | 14 |  |  |  | 7 |  |  |  | 14 | 0 | 0 | 0 | 21 | 0 | 0 | 0
| Total |  |  |  | 112 | 0 | 5 | 20 | 73 | 0 | 5 | 20 | 114.4 | 0 | 7.5 | 27 | 185 | 0 | 12.5 | 45 | 119.2667 | 0 | 7.9167 | 28.8333

## Agg
No. | Service | BackEnd man/day | DBA man/day | FrontEnd man/day | DevOps man/day | Estimation (man/days)
1 | Transactions Service | 186.4 | 39.5833 | 4.75 | 31.7667 | 262.5
2 | Booking Service | 169.1167 | 15.8333 | 0 | 18.4833 | 203.4333
3 | Policies Configuration Service | 87.1167 | 13 | 0 | 19.5 | 119.6167
4 | SPA applications | 0 | 0 | 322.9 | 15.8333 | 338.7333
5 | Hotel Service | 123.1333 | 15.8333 | 0 | 16.9 | 155.8667
6 | Transport Service | 127.9167 | 15.8333 | 0 | 14.3 | 158.05
7 | Hotel&Transport Suppliers Service | 93.0167 | 31.6667 | 0 | 18.2 | 142.8833
8 | Notifications Service | 85.8167 | 13 | 0 | 18.2 | 117.0167
9 | Reporting Service | 111.8333 | 47.5 | 0 | 17.75 | 177.0833
10 | Reactor Service | 119.2667 | 0 | 7.9167 | 28.8333 | 156.0167
| Subtotal by dev | 1103.6167 | 192.25 | 335.5667 | 199.7667
15% | VAC&SICK | 165.5425 | 28.8375 | 50.335 | 29.965
10% | Team Communication | 110.3617 | 19.225 | 33.5567 | 19.9767
5% | Code review/KT | 55.1808 | 9.6125 | 16.7783 | 9.9883
5% | Management | 55.1808 | 9.6125 | 16.7783 | 9.9883
| TOTAL by Dev | 1489.8825 | 259.5375 | 453.015 | 269.685 | 2472.12
20% | TOTAL QA | 297.9765 | 51.9075 | 90.603 | 53.937 | 494.424
No. | Service | BackEnd man/day | DBA man/day | FrontEnd man/day | DevOps man/day | Estimation (man/days)
1 | Transactions Service | 174 | 25 | 3 | 24 | 226
2 | Booking Service | 157.5 | 10 | 0 | 14 | 181.5
3 | Policies Configuration Service | 73.5 | 10 | 0 | 15 | 98.5
4 | SPA applications | 0 | 0 | 0 | 10 | 10
5 | Hotel Service | 114 | 10 | 0 | 13 | 137
6 | Transport Service | 119.5 | 10 | 0 | 11 | 140.5
7 | Hotel&Transport Suppliers Service | 82.5 | 20 | 0 | 14 | 116.5
8 | Notifications Service | 72.5 | 10 | 0 | 14 | 96.5
9 | Reporting Service | 99 | 30 | 0 | 13 | 142
10 | Reactor Service | 112 | 0 | 5 | 20 | 137
| Subtotal by dev | 1004.5 | 125 | 8 | 148
0.15 | VAC&SICK | 150.675 | 18.75 | 1.2 | 22.2
0.1 | Team Communication | 100.45 | 12.5 | 0.8 | 14.8
0.05 | Code review/KT | 50.225 | 6.25 | 0.4 | 7.4
0.05 | Management | 50.225 | 6.25 | 0.4 | 7.4
| TOTAL by Dev | 1356.075 | 168.75 | 10.8 | 199.8 | 1735.425
0.2 | TOTAL QA | 271.215 | 33.75 | 2.16 | 39.96 | 347.085

## Resource plan
Resource Plan | Total days | Project time line
Months
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Backend Team
Tech Lead | 336 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Senior Developer | 504 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Developer | 651 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4
TOTAL Backend Team | 1491 | [8 empty] | 1489.8825 | -1.1175
Frontend Team
Senior Developer | 147 | Months 2: 1; Months 3: 2; Months 4: 2; Months 5: 2
Developer | 231 | Months 2: 2; Months 3: 3; Months 4: 3; Months 5: 3
UX Designer | 84 | bar: Months 2 to Months 5
TOTAL Frontend Team | 462 | [8 empty] | 453.015 | -8.985
TOTAL DevOps | 273 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 269.685 | -3.315
TOTAL DBA | 252 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 259.5375 | 7.5375
TOTAL QA | 504 | 1 | 2 | 3 | 3 | 4 | 4 | 4 | 3 | 494.424 | -9.576
Resource Plan | Total days | Months 1: Project time line
|  | Months 1: 2025-04-01; Months 5: 2025-05-01 |  | 2025-06-01 |  |  |  | 2025-07-01 |  |  |  |  | 2025-08-01 |  |  |  | 2025-09-01 |  |  |  | 2025-10-01 |  |  |  |  | 2025-11-01
Week
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
Backend Team
Tech Lead | 345 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Senior Developer | 495 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Developer | 655 | 1 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
TOTAL Backend Team | 1495
Frontend Team
Senior Developer | 150 | Week 7: 1; Week 8: 1; Week 9: 2; Week 10: 2; Week 11: 2; Week 12: 2; Week 13: 2; Week 14: 2; Week 15: 2; Week 16: 2; Week 17: 2; Week 18: 2; Week 19: 2; Week 20: 2; Week 21: 2; Week 22: 2
Developer | 220 | Week 7: 1; Week 8: 1; Week 9: 3; Week 10: 3; Week 11: 3; Week 12: 3; Week 13: 3; Week 14: 3; Week 15: 3; Week 16: 3; Week 17: 3; Week 18: 3; Week 19: 3; Week 20: 3; Week 21: 3; Week 22: 3
UX Designer | 85 | bar: Week 5 to Week 21
TOTAL Frontend Team | 455
TOTAL DevOps | 270 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
TOTAL DBA | 260 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
TOTAL QA | 505 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Resource Plan | Total days | Week 1: Hourly Rate $; Week 2: Hours / Day; Week 3: Total by Role $
Backend Team | bar: Week 1 to Week 3
Tech Lead | 345 | Week 1: 50; Week 2: 8; Week 3: 138000
Senior Developer | 495 | Week 1: 40; Week 2: 8; Week 3: 158400
Developer | 655 | Week 1: 30; Week 2: 8; Week 3: 157200
TOTAL Backend Team | 1495
Frontend Team | bar: Week 1 to Week 2
Senior Developer | 150 | Week 1: 40; Week 2: 8; Week 3: 48000
Developer | 220 | Week 1: 35; Week 2: 8; Week 3: 61600
UX Designer | 85 | Week 1: 35; Week 2: 8; Week 3: 23800
TOTAL Frontend Team | 455
TOTAL DevOps | 270 | Week 1: 45; Week 2: 8; Week 3: 97200
TOTAL DBA | 260 | Week 1: 45; Week 2: 8; Week 3: 93600
TOTAL QA | 505 | Week 1: 30; Week 2: 8; Week 3: 121200
Total $ |  | Week 3: 899000

## Discovery_Phase_5_Day_Workshop
Time \ Day | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
| Kick-off & Context | Stakeholder Goals & Process Review | System Requirements & Tech | Architecture & Risk | Summary & Planning
09:00-10:30 | Project Kick-off (PM, CEO, DM, SA, BA, QA) | Stakeholder Interviews (BA, DM, UX) | Requirements Prioritization (BA, SA, DM) | Architecture Vision (SA, CTO, Dev Lead) | Recap & Vision Agreement (PM, All)
10:30-11:00 | Coffee Break | Coffee Break | Coffee Break | Coffee Break | Coffee Break
11:00-12:30 | Business Objectives Overview (CEO/DM, All) | Current Process Walkthrough (BA, Travel Manager, Employees, SA) | Functional Mapping (SA, BA, QA) | Risk Assessment (PM, SA, QA, DevOps) | Define MVP Scope (SA, All)
12:30-13:30 | Lunch Break | Lunch Break | Lunch Break | Lunch Break | Lunch Break
13:30-15:00 | Scope & Assumptions Validation (PM, SA, DM, BA) | User Journey Mapping (UX/BA, DM) | Non-Functional Requirements Workshop (SA, DevOps, QA) | Integration Points Review (SA, DevOps) | Resource & Timeline Planning (PM, SA, DM)
15:00-15:30 | Break | Break | Break | Break | Break
15:30-17:00 | Q&A + Logistics Setup (PM, All) | Administration Portal UX (UX, BA, Travel Manager) | Tech Stack Discussion (SA, DevOps, CTO) | Deployment & Security Considerations (DevOps, SA, QA) | Next Steps & Discovery Outcome Validation (PM, All)

## Sheet1
No. | Service | Back end | DB | DBA | UI/UX Design | Front end | Dev Ops | Total
man/day
1 | SPA Web Application | 213 | 0 | 0 | 76 | 227 | 50 | 566
2 | Prefix Management Service | 102 | 46 | 20 | 0 | 0 | 28 | 196
3 | GIN Management Service | 169 | 63 | 20 | 0 | 0 | 38 | 290
4 | Location Management Service | 153 | 63 | 20 | 0 | 0 | 38 | 274
5 | Access Data Service | 130 | 10 | 7 | 0 | 0 | 39 | 186
6 | API Gateway (Azure APIM) | 84 | 0 | 0 | 7 | 0 | 57 | 148
7 | Notification Service | 190 | 8 | 0 | 8 | 10 | 72 | 288
8 | Help & Feedback Service | 108 | 16 | 0 | 16 | 17 | 39 | 196
9 | Integration Gateway | 150 | 20 | 0 | 0 | 0 | 66 | 236
10 | Search Indexing Pipeline | 84 | 22 | 10 | 0 | 0 | 39 | 155
11 | Lightweight Reporting (ADX + Power BI) | 54 | 15 | 4 | 11 | 0 | 40 | 124
12 | Resilience & DR | 174 | 60 | 68 | 0 | 0 | 204 | 506
| Subtotal by dev | 1611 | 323 | 149 | 118 | 254 | 710
15% | VAC&SICK | 242 | 49 | 23 | 18 | 39 | 107
10% | Team Communication | 162 | 33 | 15 | 12 | 26 | 71
5% | Code review/KT | 81 | 17 | 8 | 6 | 13 | 36
5% | Management | 81 | 17 | 8 | 6 | 13 | 36
| TOTAL by Dev | 2177 | 439 | 203 | 160 | 345 | 960 | 4284
20% | TOTAL QA | 436 | 88 | 41 | 32 | 69 | 192 | 858