## solution
No. | Activity | Description | Risk level | Back end r | DB r | DBA r | UI/UX Design r | Front end r | Dev Ops r | Back end r2 | DB3 | DBA4 | UI/UX Design5 | Front end6 | Dev Ops7 | Back end8 | DB9 | DBA10 | UI/UX Design11 | Front end12 | Dev Ops13 | Back end14 | DB15 | DBA16 | UI/UX Design17 | Front end18 | Dev Ops19 | Back end | DB | DBA | UI/UX Design | Front end | Dev Ops
[10 empty] | 1 | 1 | 1 |  |  |  | 1.2 | 1.5 | 2 |  |  |  | 2 | 2.5 | 3
1 | SPA Web Application | Single Page Application providing end-user UI for all modules
| Authentication/Authorization | Handles SSO, role-based access, and permissions using claims-based auth integrated with external Identity Management (OAuth/SAML) | High | 12 | 0 | 0 | 3 | 10 | 3 | 12 | 0 | 0 | 3 | 10 | 3 | 24 | 0 | 0 | 6 | 20 | 6 | 36 | 0 | 0 | 9 | 30 | 9 | 24 | 0 | 0 | 6 | 20 | 6
| Prefixes Branch | Displays and manages Prefix data, including capacity counters and linking to product/location creation | Medium | 8 | 0 | 0 | 3 | 10 | 2 | 8 | 0 | 0 | 3 | 10 | 2 | 12 | 0 | 0 | 5 | 15 | 3 | 20 | 0 | 0 | 8 | 25 | 5 | 13 | 0 | 0 | 6 | 16 | 4
| Product Branch | Create/manage product records (GINs), images, hierarchies, barcodes, and exports | High | 15 | 0 | 0 | 4 | 14 | 3 | 15 | 0 | 0 | 4 | 14 | 3 | 30 | 0 | 0 | 8 | 28 | 6 | 45 | 0 | 0 | 12 | 42 | 9 | 30 | 0 | 0 | 8 | 28 | 6
| Location Branch | Create/manage location records (LNs), hierarchies, verification, and exports | High | 15 | 0 | 0 | 4 | 14 | 3 | 15 | 0 | 0 | 4 | 14 | 3 | 30 | 0 | 0 | 8 | 28 | 6 | 45 | 0 | 0 | 12 | 42 | 9 | 30 | 0 | 0 | 8 | 28 | 6
| Search/Reporting Branch | End-user search, filters, saved views, and report launchers | Medium | 8 | 0 | 0 | 3 | 10 | 2 | 8 | 0 | 0 | 3 | 10 | 2 | 12 | 0 | 0 | 5 | 15 | 3 | 20 | 0 | 0 | 8 | 25 | 5 | 13 | 0 | 0 | 6 | 16 | 4
| Help/Tutorials Branch | Contextual help, tutorials, and training links embedded in SPA | Low | 4 | 0 | 0 | 4 | 8 | 1 | 4 | 0 | 0 | 4 | 8 | 1 | 5 | 0 | 0 | 5 | 10 | 2 | 8 | 0 | 0 | 8 | 16 | 2 | 6 | 0 | 0 | 6 | 11 | 2
| Dashboard/Notifications | User start screen with alerts, tasks, counters, and shortcuts | Medium | 8 | 0 | 0 | 4 | 12 | 2 | 8 | 0 | 0 | 4 | 12 | 2 | 12 | 0 | 0 | 6 | 18 | 3 | 20 | 0 | 0 | 10 | 30 | 5 | 13 | 0 | 0 | 7 | 19 | 4
| Workflow Management | Record approval, status tracking, and locking UX | High | 12 | 0 | 0 | 4 | 12 | 2 | 12 | 0 | 0 | 4 | 12 | 2 | 24 | 0 | 0 | 8 | 24 | 4 | 36 | 0 | 0 | 12 | 36 | 6 | 24 | 0 | 0 | 8 | 24 | 4
| Publishing & Subscriptions | UI to publish/share data and manage subscriptions | Medium | 10 | 0 | 0 | 3 | 10 | 2 | 10 | 0 | 0 | 3 | 10 | 2 | 15 | 0 | 0 | 5 | 15 | 3 | 25 | 0 | 0 | 8 | 25 | 5 | 16 | 0 | 0 | 6 | 16 | 4
| Import/Export | Bulk import/export UX with progress, validation, and error review | Medium | 10 | 0 | 0 | 3 | 10 | 2 | 10 | 0 | 0 | 3 | 10 | 2 | 15 | 0 | 0 | 5 | 15 | 3 | 25 | 0 | 0 | 8 | 25 | 5 | 16 | 0 | 0 | 6 | 16 | 4
| Feedback Module | Capture user feedback, ratings, and route to admins | Low | 6 | 0 | 0 | 2 | 8 | 1 | 6 | 0 | 0 | 2 | 8 | 1 | 8 | 0 | 0 | 3 | 10 | 2 | 12 | 0 | 0 | 4 | 16 | 2 | 9 | 0 | 0 | 3 | 11 | 2
| Audit Trail Viewer | Display record history and change logs | Medium | 8 | 0 | 0 | 2 | 8 | 1 | 8 | 0 | 0 | 2 | 8 | 1 | 12 | 0 | 0 | 3 | 12 | 2 | 20 | 0 | 0 | 5 | 20 | 3 | 13 | 0 | 0 | 4 | 13 | 2
| Sidecar Utility Service (Frontend) | Shared client-side utilities (logging hooks, health pings, feature flags) | Low | 4 | 0 | 0 | 1 | 6 | 1 | 4 | 0 | 0 | 1 | 6 | 1 | 5 | 0 | 0 | 2 | 8 | 2 | 8 | 0 | 0 | 2 | 12 | 2 | 6 | 0 | 0 | 2 | 9 | 2
[28 empty] | 213 | 0 | 0 | 76 | 227 | 50
2 | Prefix Management Service | Handles prefix licensing, capacity tracking, and lookup for GIN/LN creation
| Prefix Store | CRUD operations for company prefixes and metadata | Medium | 12 | 6 | 3 | 0 | 0 | 2 | 12 | 6 | 3 | 0 | 0 | 2 | 18 | 9 | 5 | 0 | 0 | 3 | 30 | 15 | 8 | 0 | 0 | 5 | 19 | 10 | 6 | 0 | 0 | 4
| Capacity Tracker | Tracks usage and available capacity per prefix | Medium | 10 | 4 | 2 | 0 | 0 | 2 | 10 | 4 | 2 | 0 | 0 | 2 | 15 | 6 | 3 | 0 | 0 | 3 | 25 | 10 | 5 | 0 | 0 | 5 | 16 | 7 | 4 | 0 | 0 | 4
| Prefix Validator | Validates prefix format and compliance rules | Medium | 8 | 2 | 0 | 0 | 0 | 1 | 8 | 2 | 0 | 0 | 0 | 1 | 12 | 3 | 0 | 0 | 0 | 2 | 20 | 5 | 0 | 0 | 0 | 3 | 13 | 4 | 0 | 0 | 0 | 2
| Prefix Publish & Subscribe Engine | Manages visibility and sharing of prefix data | Medium | 10 | 2 | 0 | 0 | 0 | 2 | 10 | 2 | 0 | 0 | 0 | 2 | 15 | 3 | 0 | 0 | 0 | 3 | 25 | 5 | 0 | 0 | 0 | 5 | 16 | 4 | 0 | 0 | 0 | 4
| Prefix Search Service | Advanced search and filtering for prefix data | Medium | 8 | 2 | 0 | 0 | 0 | 1 | 8 | 2 | 0 | 0 | 0 | 1 | 12 | 3 | 0 | 0 | 0 | 2 | 20 | 5 | 0 | 0 | 0 | 3 | 13 | 4 | 0 | 0 | 0 | 2
| Prefix Import/Export Adapter | Bulk import/export of prefix records | Medium | 8 | 2 | 0 | 0 | 0 | 2 | 8 | 2 | 0 | 0 | 0 | 2 | 12 | 3 | 0 | 0 | 0 | 3 | 20 | 5 | 0 | 0 | 0 | 5 | 13 | 4 | 0 | 0 | 0 | 4
| SQL Database (Prefix) | Prefix management schema and persistence | Medium | 4 | 8 | 6 | 0 | 0 | 3 | 4 | 8 | 6 | 0 | 0 | 3 | 6 | 12 | 9 | 0 | 0 | 5 | 10 | 20 | 15 | 0 | 0 | 8 | 7 | 13 | 10 | 0 | 0 | 6
| Key Vault Reader | Secure retrieval of secrets/credentials | Low | 3 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 2 | 6 | 0 | 0 | 0 | 0 | 2 | 5 | 0 | 0 | 0 | 0 | 2
[28 empty] | 102 | 46 | 20 | 0 | 0 | 28
3 | GIN Management Service | Manages creation, editing, hierarchy, sharing of GINs and product metadata
| GIN Store | CRUD for product records and GINs | High | 14 | 6 | 3 | 0 | 0 | 2 | 14 | 6 | 3 | 0 | 0 | 2 | 28 | 12 | 6 | 0 | 0 | 4 | 42 | 18 | 9 | 0 | 0 | 6 | 28 | 12 | 6 | 0 | 0 | 4
| GIN Assignment Engine | Auto/manual assignment with check-digit | High | 12 | 4 | 2 | 0 | 0 | 2 | 12 | 4 | 2 | 0 | 0 | 2 | 24 | 8 | 4 | 0 | 0 | 4 | 36 | 12 | 6 | 0 | 0 | 6 | 24 | 8 | 4 | 0 | 0 | 4
| GIN Validator | Validates GINs and product attributes | Medium | 8 | 3 | 0 | 0 | 0 | 1 | 8 | 3 | 0 | 0 | 0 | 1 | 12 | 5 | 0 | 0 | 0 | 2 | 20 | 8 | 0 | 0 | 0 | 3 | 13 | 6 | 0 | 0 | 0 | 2
| Hierarchy Manager (GIN) | Build/manage product hierarchies | High | 12 | 4 | 0 | 0 | 0 | 2 | 12 | 4 | 0 | 0 | 0 | 2 | 24 | 8 | 0 | 0 | 0 | 4 | 36 | 12 | 0 | 0 | 0 | 6 | 24 | 8 | 0 | 0 | 0 | 4
| Image Attachment Service | Upload and manage product images | Medium | 8 | 2 | 0 | 0 | 0 | 1 | 8 | 2 | 0 | 0 | 0 | 1 | 12 | 3 | 0 | 0 | 0 | 2 | 20 | 5 | 0 | 0 | 0 | 3 | 13 | 4 | 0 | 0 | 0 | 2
| Export & Sheet Generator | Generate product sheets and barcodes | Medium | 10 | 2 | 0 | 0 | 0 | 2 | 10 | 2 | 0 | 0 | 0 | 2 | 15 | 3 | 0 | 0 | 0 | 3 | 25 | 5 | 0 | 0 | 0 | 5 | 16 | 4 | 0 | 0 | 0 | 4
| Barcode Generator | Create standard-compliant barcodes (PNG/SVG/PDF) | Medium | 8 | 0 | 0 | 0 | 0 | 1 | 8 | 0 | 0 | 0 | 0 | 1 | 12 | 0 | 0 | 0 | 0 | 2 | 20 | 0 | 0 | 0 | 0 | 3 | 13 | 0 | 0 | 0 | 0 | 2
| Publish & Transfer Module | Publishing and ownership transfer | Medium | 8 | 2 | 0 | 0 | 0 | 2 | 8 | 2 | 0 | 0 | 0 | 2 | 12 | 3 | 0 | 0 | 0 | 3 | 20 | 5 | 0 | 0 | 0 | 5 | 13 | 4 | 0 | 0 | 0 | 4
| GIN Import Adapter | Import via Excel/CSV/XML with dedupe | Medium | 8 | 2 | 0 | 0 | 0 | 2 | 8 | 2 | 0 | 0 | 0 | 2 | 12 | 3 | 0 | 0 | 0 | 3 | 20 | 5 | 0 | 0 | 0 | 5 | 13 | 4 | 0 | 0 | 0 | 4
| SQL Database (GIN) | Product/Gin schema and persistence | Medium | 4 | 8 | 6 | 0 | 0 | 3 | 4 | 8 | 6 | 0 | 0 | 3 | 6 | 12 | 9 | 0 | 0 | 5 | 10 | 20 | 15 | 0 | 0 | 8 | 7 | 13 | 10 | 0 | 0 | 6
| Key Vault Reader | Secrets for image/barcode/export services | Low | 3 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 2 | 6 | 0 | 0 | 0 | 0 | 2 | 5 | 0 | 0 | 0 | 0 | 2
[28 empty] | 169 | 63 | 20 | 0 | 0 | 38
4 | Location Management Service | Manages creation, editing, hierarchy, sharing of LNs and location metadata
| Location Store | CRUD for location records and LNs | High | 14 | 6 | 3 | 0 | 0 | 2 | 14 | 6 | 3 | 0 | 0 | 2 | 28 | 12 | 6 | 0 | 0 | 4 | 42 | 18 | 9 | 0 | 0 | 6 | 28 | 12 | 6 | 0 | 0 | 4
| LN Assignment Engine | Auto/manual LN assignment with check-digit | High | 12 | 4 | 2 | 0 | 0 | 2 | 12 | 4 | 2 | 0 | 0 | 2 | 24 | 8 | 4 | 0 | 0 | 4 | 36 | 12 | 6 | 0 | 0 | 6 | 24 | 8 | 4 | 0 | 0 | 4
| Location Validator | Validates LNs and attributes | Medium | 8 | 3 | 0 | 0 | 0 | 1 | 8 | 3 | 0 | 0 | 0 | 1 | 12 | 5 | 0 | 0 | 0 | 2 | 20 | 8 | 0 | 0 | 0 | 3 | 13 | 6 | 0 | 0 | 0 | 2
| Hierarchy Manager (Location) | Build/manage location hierarchies | High | 12 | 4 | 0 | 0 | 0 | 2 | 12 | 4 | 0 | 0 | 0 | 2 | 24 | 8 | 0 | 0 | 0 | 4 | 36 | 12 | 0 | 0 | 0 | 6 | 24 | 8 | 0 | 0 | 0 | 4
| Location Import Adapter | Import via Excel/CSV/XML with dedupe | Medium | 8 | 2 | 0 | 0 | 0 | 2 | 8 | 2 | 0 | 0 | 0 | 2 | 12 | 3 | 0 | 0 | 0 | 3 | 20 | 5 | 0 | 0 | 0 | 5 | 13 | 4 | 0 | 0 | 0 | 4
| Export & Reporting Module | Exports and simple reports for LNs | Medium | 8 | 2 | 0 | 0 | 0 | 2 | 8 | 2 | 0 | 0 | 0 | 2 | 12 | 3 | 0 | 0 | 0 | 3 | 20 | 5 | 0 | 0 | 0 | 5 | 13 | 4 | 0 | 0 | 0 | 4
| Publish & Transfer Module | Publishing and ownership transfer | Medium | 8 | 2 | 0 | 0 | 0 | 2 | 8 | 2 | 0 | 0 | 0 | 2 | 12 | 3 | 0 | 0 | 0 | 3 | 20 | 5 | 0 | 0 | 0 | 5 | 13 | 4 | 0 | 0 | 0 | 4
| Annual Verification Engine | Tracks/enforces annual verification | Medium | 8 | 2 | 0 | 0 | 0 | 2 | 8 | 2 | 0 | 0 | 0 | 2 | 12 | 3 | 0 | 0 | 0 | 3 | 20 | 5 | 0 | 0 | 0 | 5 | 13 | 4 | 0 | 0 | 0 | 4
| SQL Database (Location) | Location/LN schema and persistence | Medium | 4 | 8 | 6 | 0 | 0 | 3 | 4 | 8 | 6 | 0 | 0 | 3 | 6 | 12 | 9 | 0 | 0 | 5 | 10 | 20 | 15 | 0 | 0 | 8 | 7 | 13 | 10 | 0 | 0 | 6
| Key Vault Reader | Secrets for adapters/exports | Low | 3 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 2 | 6 | 0 | 0 | 0 | 0 | 2 | 5 | 0 | 0 | 0 | 0 | 2
[28 empty] | 153 | 63 | 20 | 0 | 0 | 38
5 | Access Data Service | Provides search, view, subscription, and export functionality for shared Prefix, GIN, and LN data
| Access Search Engine | Performs advanced search and filtering across Prefix, GIN, and LN datasets | Medium | 10 | 0 | 0 | 0 | 0 | 2 | 10 | 0 | 0 | 0 | 0 | 2 | 15 | 0 | 0 | 0 | 0 | 3 | 25 | 0 | 0 | 0 | 0 | 5 | 16 | 0 | 0 | 0 | 0 | 4
| Record Viewer | Displays record details, including basic/full data and hierarchy | Medium | 8 | 0 | 0 | 0 | 0 | 2 | 8 | 0 | 0 | 0 | 0 | 2 | 12 | 0 | 0 | 0 | 0 | 3 | 20 | 0 | 0 | 0 | 0 | 5 | 13 | 0 | 0 | 0 | 0 | 4
| Subscription Manager | Handles subscription requests for accessing full record views | High | 15 | 0 | 0 | 0 | 0 | 3 | 15 | 0 | 0 | 0 | 0 | 3 | 30 | 0 | 0 | 0 | 0 | 6 | 45 | 0 | 0 | 0 | 0 | 9 | 30 | 0 | 0 | 0 | 0 | 6
| Group Access Controller | Processes join requests for controlled groups | Medium | 8 | 0 | 0 | 0 | 0 | 2 | 8 | 0 | 0 | 0 | 0 | 2 | 12 | 0 | 0 | 0 | 0 | 3 | 20 | 0 | 0 | 0 | 0 | 5 | 13 | 0 | 0 | 0 | 0 | 4
| Export Adapter | Exports records to CSV/Excel/XML and prints | Medium | 8 | 0 | 0 | 0 | 0 | 2 | 8 | 0 | 0 | 0 | 0 | 2 | 12 | 0 | 0 | 0 | 0 | 3 | 20 | 0 | 0 | 0 | 0 | 5 | 13 | 0 | 0 | 0 | 0 | 4
| Access Rights Evaluator | Determines view level based on roles/subscriptions | High | 12 | 0 | 0 | 0 | 0 | 3 | 12 | 0 | 0 | 0 | 0 | 3 | 24 | 0 | 0 | 0 | 0 | 6 | 36 | 0 | 0 | 0 | 0 | 9 | 24 | 0 | 0 | 0 | 0 | 6
| Ad-hoc Access Info Module | Surfaces payment info for ad-hoc access (out of scope payments) | Low | 4 | 0 | 0 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 2 | 8 | 0 | 0 | 0 | 0 | 2 | 6 | 0 | 0 | 0 | 0 | 2
| Read-Optimized Store (Elasticsearch) | Indexed shared data optimized for queries | Medium | 6 | 6 | 4 | 0 | 0 | 4 | 6 | 6 | 4 | 0 | 0 | 4 | 9 | 9 | 6 | 0 | 0 | 6 | 15 | 15 | 10 | 0 | 0 | 10 | 10 | 10 | 7 | 0 | 0 | 7
| Key Vault Reader | Secrets for export/index access | Low | 3 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 2 | 6 | 0 | 0 | 0 | 0 | 2 | 5 | 0 | 0 | 0 | 0 | 2
[28 empty] | 130 | 10 | 7 | 0 | 0 | 39
6 | API Gateway (Azure APIM) | Central API entry; policies, routing, throttling, analytics; migration from 3Scale
| 3Scale Config Migrator | Migrate definitions, plans, policies to APIM | High | 12 | 0 | 0 | 0 | 0 | 8 | 12 | 0 | 0 | 0 | 0 | 8 | 24 | 0 | 0 | 0 | 0 | 16 | 36 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 16
| API Router | Route to internal services by path/version | Medium | 8 | 0 | 0 | 0 | 0 | 5 | 8 | 0 | 0 | 0 | 0 | 5 | 12 | 0 | 0 | 0 | 0 | 8 | 20 | 0 | 0 | 0 | 0 | 13 | 13 | 0 | 0 | 0 | 0 | 9
| Policy Enforcement Engine | JWT, quota, CORS, caching, IP filtering | High | 12 | 0 | 0 | 0 | 0 | 8 | 12 | 0 | 0 | 0 | 0 | 8 | 24 | 0 | 0 | 0 | 0 | 16 | 36 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 16
| Telemetry & Analytics Module | Collect usage metrics and errors | Medium | 6 | 0 | 0 | 0 | 0 | 5 | 6 | 0 | 0 | 0 | 0 | 5 | 9 | 0 | 0 | 0 | 0 | 8 | 15 | 0 | 0 | 0 | 0 | 13 | 10 | 0 | 0 | 0 | 0 | 9
| Developer Portal | Docs, try-it, subscription keys | Medium | 8 | 0 | 0 | 4 | 0 | 4 | 8 | 0 | 0 | 4 | 0 | 4 | 12 | 0 | 0 | 6 | 0 | 6 | 20 | 0 | 0 | 10 | 0 | 10 | 13 | 0 | 0 | 7 | 0 | 7
[28 empty] | 84 | 0 | 0 | 7 | 0 | 57
7 | Notification Service | Multi-channel notifications (email, SMS, push, in-app) with templates and preferences
| EventHub Consumer | Consumes events and creates notification intents | Medium | 8 | 0 | 0 | 0 | 0 | 3 | 8 | 0 | 0 | 0 | 0 | 3 | 12 | 0 | 0 | 0 | 0 | 5 | 20 | 0 | 0 | 0 | 0 | 8 | 13 | 0 | 0 | 0 | 0 | 6
| Notification Orchestrator | Routing, rules, multi-channel fan-out | High | 12 | 0 | 0 | 0 | 0 | 4 | 12 | 0 | 0 | 0 | 0 | 4 | 24 | 0 | 0 | 0 | 0 | 8 | 36 | 0 | 0 | 0 | 0 | 12 | 24 | 0 | 0 | 0 | 0 | 8
| Template & Localization Engine | Render content with variables and i18n | Medium | 8 | 0 | 0 | 2 | 0 | 2 | 8 | 0 | 0 | 2 | 0 | 2 | 12 | 0 | 0 | 3 | 0 | 3 | 20 | 0 | 0 | 5 | 0 | 5 | 13 | 0 | 0 | 4 | 0 | 4
| Preference & Opt-In Manager | User/company preferences and quiet hours | Medium | 8 | 2 | 0 | 0 | 0 | 2 | 8 | 2 | 0 | 0 | 0 | 2 | 12 | 3 | 0 | 0 | 0 | 3 | 20 | 5 | 0 | 0 | 0 | 5 | 13 | 4 | 0 | 0 | 0 | 4
| Topic & Subscription Router | Targeted delivery by topic/group | Medium | 8 | 0 | 0 | 0 | 0 | 2 | 8 | 0 | 0 | 0 | 0 | 2 | 12 | 0 | 0 | 0 | 0 | 3 | 20 | 0 | 0 | 0 | 0 | 5 | 13 | 0 | 0 | 0 | 0 | 4
| Policy & Rate Limit Engine | Throttling, dedupe, suppression | Medium | 8 | 0 | 0 | 0 | 0 | 2 | 8 | 0 | 0 | 0 | 0 | 2 | 12 | 0 | 0 | 0 | 0 | 3 | 20 | 0 | 0 | 0 | 0 | 5 | 13 | 0 | 0 | 0 | 0 | 4
| Retry & DLQ Processor | Retries and dead-letter handling | Medium | 6 | 0 | 0 | 0 | 0 | 2 | 6 | 0 | 0 | 0 | 0 | 2 | 9 | 0 | 0 | 0 | 0 | 3 | 15 | 0 | 0 | 0 | 0 | 5 | 10 | 0 | 0 | 0 | 0 | 4
| Delivery Status & Bounce Tracker | Track sends, opens, bounces | Medium | 6 | 0 | 0 | 0 | 0 | 2 | 6 | 0 | 0 | 0 | 0 | 2 | 9 | 0 | 0 | 0 | 0 | 3 | 15 | 0 | 0 | 0 | 0 | 5 | 10 | 0 | 0 | 0 | 0 | 4
| In-App Notification Hub | WebSocket/WebPush delivery + unread state | Medium | 8 | 0 | 0 | 2 | 6 | 3 | 8 | 0 | 0 | 2 | 6 | 3 | 12 | 0 | 0 | 3 | 9 | 5 | 20 | 0 | 0 | 5 | 15 | 8 | 13 | 0 | 0 | 4 | 10 | 6
| Email Adapter | Send via ACS/SMTP | Low | 5 | 0 | 0 | 0 | 0 | 2 | 5 | 0 | 0 | 0 | 0 | 2 | 6 | 0 | 0 | 0 | 0 | 3 | 10 | 0 | 0 | 0 | 0 | 4 | 7 | 0 | 0 | 0 | 0 | 3
| SMS Adapter | Send via ACS/Twilio | Low | 5 | 0 | 0 | 0 | 0 | 2 | 5 | 0 | 0 | 0 | 0 | 2 | 6 | 0 | 0 | 0 | 0 | 3 | 10 | 0 | 0 | 0 | 0 | 4 | 7 | 0 | 0 | 0 | 0 | 3
| Mobile/Web Push Adapter | Push via FCM/APNS/WebPush | Low | 6 | 0 | 0 | 0 | 0 | 2 | 6 | 0 | 0 | 0 | 0 | 2 | 8 | 0 | 0 | 0 | 0 | 3 | 12 | 0 | 0 | 0 | 0 | 4 | 9 | 0 | 0 | 0 | 0 | 3
| Webhook/ChatOps Adapter | Slack/Teams/webhooks for ops | Low | 5 | 0 | 0 | 0 | 0 | 2 | 5 | 0 | 0 | 0 | 0 | 2 | 6 | 0 | 0 | 0 | 0 | 3 | 10 | 0 | 0 | 0 | 0 | 4 | 7 | 0 | 0 | 0 | 0 | 3
| Digest & Scheduling Service | Schedules digests/reminders | Medium | 6 | 0 | 0 | 0 | 0 | 2 | 6 | 0 | 0 | 0 | 0 | 2 | 9 | 0 | 0 | 0 | 0 | 3 | 15 | 0 | 0 | 0 | 0 | 5 | 10 | 0 | 0 | 0 | 0 | 4
| Notification API | APIs for intents/templates/preferences | Medium | 8 | 0 | 0 | 0 | 0 | 3 | 8 | 0 | 0 | 0 | 0 | 3 | 12 | 0 | 0 | 0 | 0 | 5 | 20 | 0 | 0 | 0 | 0 | 8 | 13 | 0 | 0 | 0 | 0 | 6
| Key Vault Reader | Secrets and credentials | Low | 3 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 2 | 6 | 0 | 0 | 0 | 0 | 2 | 5 | 0 | 0 | 0 | 0 | 2
| Audit & Compliance Logger | Immutable audit for notifications | Medium | 6 | 2 | 0 | 0 | 0 | 2 | 6 | 2 | 0 | 0 | 0 | 2 | 9 | 3 | 0 | 0 | 0 | 3 | 15 | 5 | 0 | 0 | 0 | 5 | 10 | 4 | 0 | 0 | 0 | 4
[28 empty] | 190 | 8 | 0 | 8 | 10 | 72
8 | Help & Feedback Service | Help content, tutorials, search, localization, and feedback capture
| Help Content Manager | CRUD for articles, FAQs, tutorials | Medium | 8 | 2 | 0 | 2 | 0 | 2 | 8 | 2 | 0 | 2 | 0 | 2 | 12 | 3 | 0 | 3 | 0 | 3 | 20 | 5 | 0 | 5 | 0 | 5 | 13 | 4 | 0 | 4 | 0 | 4
| Help Media Storage | Store videos, images, docs | Low | 4 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 2 | 5 | 0 | 0 | 0 | 0 | 3 | 8 | 0 | 0 | 0 | 0 | 4 | 6 | 0 | 0 | 0 | 0 | 3
| Help Search Engine | Index and query help content | Medium | 6 | 2 | 0 | 0 | 0 | 2 | 6 | 2 | 0 | 0 | 0 | 2 | 9 | 3 | 0 | 0 | 0 | 3 | 15 | 5 | 0 | 0 | 0 | 5 | 10 | 4 | 0 | 0 | 0 | 4
| Contextual Help Resolver | Serve context-aware help items | Medium | 6 | 0 | 0 | 2 | 4 | 2 | 6 | 0 | 0 | 2 | 4 | 2 | 9 | 0 | 0 | 3 | 6 | 3 | 15 | 0 | 0 | 5 | 10 | 5 | 10 | 0 | 0 | 4 | 7 | 4
| Help Localization Engine | Localized content support | Medium | 6 | 0 | 0 | 2 | 0 | 1 | 6 | 0 | 0 | 2 | 0 | 1 | 9 | 0 | 0 | 3 | 0 | 2 | 15 | 0 | 0 | 5 | 0 | 3 | 10 | 0 | 0 | 4 | 0 | 2
| Feedback Collector | Capture comments/ratings/issues | Medium | 6 | 0 | 0 | 2 | 6 | 2 | 6 | 0 | 0 | 2 | 6 | 2 | 9 | 0 | 0 | 3 | 9 | 3 | 15 | 0 | 0 | 5 | 15 | 5 | 10 | 0 | 0 | 4 | 10 | 4
| Feedback Router | Route feedback to admins/teams | Low | 4 | 0 | 0 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 2 | 8 | 0 | 0 | 0 | 0 | 2 | 6 | 0 | 0 | 0 | 0 | 2
| Feedback Analytics | Aggregate and analyze feedback | Medium | 6 | 2 | 0 | 0 | 0 | 2 | 6 | 2 | 0 | 0 | 0 | 2 | 9 | 3 | 0 | 0 | 0 | 3 | 15 | 5 | 0 | 0 | 0 | 5 | 10 | 4 | 0 | 0 | 0 | 4
| Feedback Notification | Notify admins on new/critical items | Low | 4 | 0 | 0 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 2 | 8 | 0 | 0 | 0 | 0 | 2 | 6 | 0 | 0 | 0 | 0 | 2
| Help & Feedback API | REST endpoints for help/feedback | Medium | 8 | 0 | 0 | 0 | 0 | 2 | 8 | 0 | 0 | 0 | 0 | 2 | 12 | 0 | 0 | 0 | 0 | 3 | 20 | 0 | 0 | 0 | 0 | 5 | 13 | 0 | 0 | 0 | 0 | 4
| Key Vault Reader | Secrets for integrations | Low | 3 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 2 | 6 | 0 | 0 | 0 | 0 | 2 | 5 | 0 | 0 | 0 | 0 | 2
| Audit Logger | Record content and admin changes | Medium | 5 | 2 | 0 | 0 | 0 | 2 | 5 | 2 | 0 | 0 | 0 | 2 | 8 | 3 | 0 | 0 | 0 | 3 | 13 | 5 | 0 | 0 | 0 | 5 | 9 | 4 | 0 | 0 | 0 | 4
[28 empty] | 108 | 16 | 0 | 16 | 17 | 39
9 | Integration Gateway | Adapters and pipelines for SAP and QuickBooks integrations
| Integration Gateway API | Central API for imports/exports | Medium | 8 | 0 | 0 | 0 | 0 | 3 | 8 | 0 | 0 | 0 | 0 | 3 | 12 | 0 | 0 | 0 | 0 | 5 | 20 | 0 | 0 | 0 | 0 | 8 | 13 | 0 | 0 | 0 | 0 | 6
| SAP Adapter | IDoc/XML/JSON via SAP PI/PO or APIs | High | 14 | 2 | 0 | 0 | 0 | 8 | 14 | 2 | 0 | 0 | 0 | 8 | 28 | 4 | 0 | 0 | 0 | 16 | 42 | 6 | 0 | 0 | 0 | 24 | 28 | 4 | 0 | 0 | 0 | 16
| QuickBooks Adapter | QBO/QBD API/SDK sync | High | 12 | 2 | 0 | 0 | 0 | 6 | 12 | 2 | 0 | 0 | 0 | 6 | 24 | 4 | 0 | 0 | 0 | 12 | 36 | 6 | 0 | 0 | 0 | 18 | 24 | 4 | 0 | 0 | 0 | 12
| Data Mapping & Transformation Engine | Map internal‚Üîexternal schemas | High | 12 | 2 | 0 | 0 | 0 | 4 | 12 | 2 | 0 | 0 | 0 | 4 | 24 | 4 | 0 | 0 | 0 | 8 | 36 | 6 | 0 | 0 | 0 | 12 | 24 | 4 | 0 | 0 | 0 | 8
| Validation & Compliance Engine | Validate against standards/rules | Medium | 8 | 2 | 0 | 0 | 0 | 2 | 8 | 2 | 0 | 0 | 0 | 2 | 12 | 3 | 0 | 0 | 0 | 3 | 20 | 5 | 0 | 0 | 0 | 5 | 13 | 4 | 0 | 0 | 0 | 4
| Integration Scheduler | Batch job coordination | Medium | 6 | 0 | 0 | 0 | 0 | 2 | 6 | 0 | 0 | 0 | 0 | 2 | 9 | 0 | 0 | 0 | 0 | 3 | 15 | 0 | 0 | 0 | 0 | 5 | 10 | 0 | 0 | 0 | 0 | 4
| Change Event Publisher | Publish webhooks/queues to externals | Medium | 8 | 0 | 0 | 0 | 0 | 3 | 8 | 0 | 0 | 0 | 0 | 3 | 12 | 0 | 0 | 0 | 0 | 5 | 20 | 0 | 0 | 0 | 0 | 8 | 13 | 0 | 0 | 0 | 0 | 6
| Error Handling & Retry Manager | Retries/backoff and logging | Medium | 6 | 0 | 0 | 0 | 0 | 2 | 6 | 0 | 0 | 0 | 0 | 2 | 9 | 0 | 0 | 0 | 0 | 3 | 15 | 0 | 0 | 0 | 0 | 5 | 10 | 0 | 0 | 0 | 0 | 4
| Integration Audit Logger | Full transaction logging | Medium | 6 | 2 | 0 | 0 | 0 | 2 | 6 | 2 | 0 | 0 | 0 | 2 | 9 | 3 | 0 | 0 | 0 | 3 | 15 | 5 | 0 | 0 | 0 | 5 | 10 | 4 | 0 | 0 | 0 | 4
| Key Vault Reader | External creds/certs | Low | 3 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 2 | 6 | 0 | 0 | 0 | 0 | 2 | 5 | 0 | 0 | 0 | 0 | 2
[28 empty] | 150 | 20 | 0 | 0 | 0 | 66
10 | Search Indexing Pipeline | Consumes CDC events and indexes denormalized docs into Elasticsearch
| Event Consumer | Subscribe to gin.*, location.*, prefix.\* | Medium | 8 | 0 | 0 | 0 | 0 | 3 | 8 | 0 | 0 | 0 | 0 | 3 | 12 | 0 | 0 | 0 | 0 | 5 | 20 | 0 | 0 | 0 | 0 | 8 | 13 | 0 | 0 | 0 | 0 | 6
| Denormalizer | Flatten graph/hierarchy to search docs | High | 12 | 2 | 0 | 0 | 0 | 4 | 12 | 2 | 0 | 0 | 0 | 4 | 24 | 4 | 0 | 0 | 0 | 8 | 36 | 6 | 0 | 0 | 0 | 12 | 24 | 4 | 0 | 0 | 0 | 8
| Idempotency Store | Track processed event versions | Medium | 6 | 2 | 0 | 0 | 0 | 2 | 6 | 2 | 0 | 0 | 0 | 2 | 9 | 3 | 0 | 0 | 0 | 3 | 15 | 5 | 0 | 0 | 0 | 5 | 10 | 4 | 0 | 0 | 0 | 4
| Elasticsearch Bulk Indexer | Batch upserts/deletes with backoff | High | 12 | 2 | 0 | 0 | 0 | 4 | 12 | 2 | 0 | 0 | 0 | 4 | 24 | 4 | 0 | 0 | 0 | 8 | 36 | 6 | 0 | 0 | 0 | 12 | 24 | 4 | 0 | 0 | 0 | 8
| Dead Letter Queue | Hold poison messages for replay | Low | 4 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 2 | 5 | 0 | 0 | 0 | 0 | 3 | 8 | 0 | 0 | 0 | 0 | 4 | 6 | 0 | 0 | 0 | 0 | 3
| Elasticsearch Cluster | Search indices & aliases | Medium | 4 | 6 | 6 | 0 | 0 | 6 | 4 | 6 | 6 | 0 | 0 | 6 | 6 | 9 | 9 | 0 | 0 | 9 | 10 | 15 | 15 | 0 | 0 | 15 | 7 | 10 | 10 | 0 | 0 | 10
[28 empty] | 84 | 22 | 10 | 0 | 0 | 39
11 | Lightweight Reporting (ADX + Power BI) | Near real-time API usage analytics via Log Analytics ‚Üí ADX, served in Power BI
| APIM Diagnostic Settings | Emit request logs and metrics | Low | 3 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 4 | 6 | 0 | 0 | 0 | 0 | 6 | 5 | 0 | 0 | 0 | 0 | 5
| Log Analytics Exporter | Continuous export to ADX | Medium | 6 | 2 | 0 | 0 | 0 | 4 | 6 | 2 | 0 | 0 | 0 | 4 | 9 | 3 | 0 | 0 | 0 | 6 | 15 | 5 | 0 | 0 | 0 | 10 | 10 | 4 | 0 | 0 | 0 | 7
| Event Hub Ingest (optional) | Stream diagnostics to ADX | Medium | 6 | 0 | 0 | 0 | 0 | 4 | 6 | 0 | 0 | 0 | 0 | 4 | 9 | 0 | 0 | 0 | 0 | 6 | 15 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 7
| ADX Database & Tables | Kusto tables with policies | Medium | 4 | 4 | 2 | 0 | 0 | 4 | 4 | 4 | 2 | 0 | 0 | 4 | 6 | 6 | 3 | 0 | 0 | 6 | 10 | 10 | 5 | 0 | 0 | 10 | 7 | 7 | 4 | 0 | 0 | 7
| ADX Update Policies | Materialize rollups and parsing | Medium | 5 | 2 | 0 | 0 | 0 | 3 | 5 | 2 | 0 | 0 | 0 | 3 | 8 | 3 | 0 | 0 | 0 | 5 | 13 | 5 | 0 | 0 | 0 | 8 | 9 | 4 | 0 | 0 | 0 | 6
| Power BI Semantic Model | Datasets/measures with RLS | Medium | 4 | 0 | 0 | 2 | 0 | 2 | 4 | 0 | 0 | 2 | 0 | 2 | 6 | 0 | 0 | 3 | 0 | 3 | 10 | 0 | 0 | 5 | 0 | 5 | 7 | 0 | 0 | 4 | 0 | 4
| Power BI Reports & Dashboards | Usage heatmaps, SLAs, errors | Medium | 3 | 0 | 0 | 4 | 0 | 2 | 3 | 0 | 0 | 4 | 0 | 2 | 5 | 0 | 0 | 6 | 0 | 3 | 8 | 0 | 0 | 10 | 0 | 5 | 6 | 0 | 0 | 7 | 0 | 4
[28 empty] | 54 | 15 | 4 | 11 | 0 | 40
12 | Resilience & DR | Cross-region HA/DR, backups, automation, and chaos validation
| Azure Front Door (Global) | Anycast entry, WAF, health probes | Medium | 6 | 0 | 0 | 0 | 0 | 8 | 6 | 0 | 0 | 0 | 0 | 8 | 9 | 0 | 0 | 0 | 0 | 12 | 15 | 0 | 0 | 0 | 0 | 20 | 10 | 0 | 0 | 0 | 0 | 13
| Traffic Manager (Optional) | DNS failover for non-HTTP endpoints | Low | 4 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 4 | 5 | 0 | 0 | 0 | 0 | 5 | 8 | 0 | 0 | 0 | 0 | 8 | 6 | 0 | 0 | 0 | 0 | 6
| APIM - Region A | Primary gateway (Premium) | Medium | 6 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 6 | 9 | 0 | 0 | 0 | 0 | 9 | 15 | 0 | 0 | 0 | 0 | 15 | 10 | 0 | 0 | 0 | 0 | 10
| APIM - Region B | Secondary gateway (Premium) | Medium | 6 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 6 | 9 | 0 | 0 | 0 | 0 | 9 | 15 | 0 | 0 | 0 | 0 | 15 | 10 | 0 | 0 | 0 | 0 | 10
| App Tier - Region A | Stateless apps/functions (active) | Medium | 6 | 0 | 0 | 0 | 0 | 5 | 6 | 0 | 0 | 0 | 0 | 5 | 9 | 0 | 0 | 0 | 0 | 8 | 15 | 0 | 0 | 0 | 0 | 13 | 10 | 0 | 0 | 0 | 0 | 9
| App Tier - Region B | Stateless apps/functions (warm/active) | Medium | 6 | 0 | 0 | 0 | 0 | 5 | 6 | 0 | 0 | 0 | 0 | 5 | 9 | 0 | 0 | 0 | 0 | 8 | 15 | 0 | 0 | 0 | 0 | 13 | 10 | 0 | 0 | 0 | 0 | 9
| Cosmos DB (Multi-Write) | Multi-region writes, auto failover | High | 6 | 8 | 6 | 0 | 0 | 8 | 6 | 8 | 6 | 0 | 0 | 8 | 12 | 16 | 12 | 0 | 0 | 16 | 18 | 24 | 18 | 0 | 0 | 24 | 12 | 16 | 12 | 0 | 0 | 16
| Azure SQL (Failover Group) | Geo-replicated with listener | High | 6 | 8 | 8 | 0 | 0 | 8 | 6 | 8 | 8 | 0 | 0 | 8 | 12 | 16 | 16 | 0 | 0 | 16 | 18 | 24 | 24 | 0 | 0 | 24 | 12 | 16 | 16 | 0 | 0 | 16
| Event Hubs (Geo-DR Alias) | Paired namespaces with alias | High | 6 | 2 | 4 | 0 | 0 | 8 | 6 | 2 | 4 | 0 | 0 | 8 | 12 | 4 | 8 | 0 | 0 | 16 | 18 | 6 | 12 | 0 | 0 | 24 | 12 | 4 | 8 | 0 | 0 | 16
| Service Bus (Geo-DR) | Paired namespaces/alias | High | 6 | 2 | 4 | 0 | 0 | 8 | 6 | 2 | 4 | 0 | 0 | 8 | 12 | 4 | 8 | 0 | 0 | 16 | 18 | 6 | 12 | 0 | 0 | 24 | 12 | 4 | 8 | 0 | 0 | 16
| Blob Storage (RA-GZRS) | Geo-redundant, read-access | Medium | 4 | 2 | 2 | 0 | 0 | 4 | 4 | 2 | 2 | 0 | 0 | 4 | 6 | 3 | 3 | 0 | 0 | 6 | 10 | 5 | 5 | 0 | 0 | 10 | 7 | 4 | 4 | 0 | 0 | 7
| Elasticsearch (CCR) | Cross-cluster replication | High | 6 | 4 | 6 | 0 | 0 | 8 | 6 | 4 | 6 | 0 | 0 | 8 | 12 | 8 | 12 | 0 | 0 | 16 | 18 | 12 | 18 | 0 | 0 | 24 | 12 | 8 | 12 | 0 | 0 | 16
| ADX (Follower DB) | Follower DB for DR | Medium | 4 | 2 | 2 | 0 | 0 | 5 | 4 | 2 | 2 | 0 | 0 | 5 | 6 | 3 | 3 | 0 | 0 | 8 | 10 | 5 | 5 | 0 | 0 | 13 | 7 | 4 | 4 | 0 | 0 | 9
| Key Vault (Geo) | Geo-replicated, purge protection | Medium | 4 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 4 | 6 | 0 | 0 | 0 | 0 | 6 | 10 | 0 | 0 | 0 | 0 | 10 | 7 | 0 | 0 | 0 | 0 | 7
| ASR/Backup | Backups and runbook ties | Medium | 4 | 2 | 2 | 0 | 0 | 6 | 4 | 2 | 2 | 0 | 0 | 6 | 6 | 3 | 3 | 0 | 0 | 9 | 10 | 5 | 5 | 0 | 0 | 15 | 7 | 4 | 4 | 0 | 0 | 10
| Log Analytics + App Insights | Telemetry and alerts | Medium | 4 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 4 | 6 | 0 | 0 | 0 | 0 | 6 | 10 | 0 | 0 | 0 | 0 | 10 | 7 | 0 | 0 | 0 | 0 | 7
| Failover Runbooks (Automation) | One-click failover orchestration | High | 8 | 0 | 0 | 0 | 0 | 10 | 8 | 0 | 0 | 0 | 0 | 10 | 16 | 0 | 0 | 0 | 0 | 20 | 24 | 0 | 0 | 0 | 0 | 30 | 16 | 0 | 0 | 0 | 0 | 20
| Chaos Studio | Fault injection and game days | Medium | 4 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 4 | 6 | 0 | 0 | 0 | 0 | 6 | 10 | 0 | 0 | 0 | 0 | 10 | 7 | 0 | 0 | 0 | 0 | 7
[28 empty] | 174 | 60 | 68 | 0 | 0 | 204

## Agg
No. | Service | Back end | DB | DBA | UI/UX Design | Front end | Dev Ops | Total
man/day
1 | SPA Web Application | 213 | 0 | 0 | 76 | 227 | 50 | 566
2 | Prefix Management Service | 102 | 46 | 20 | 0 | 0 | 28 | 196
3 | GIN Management Service | 169 | 63 | 20 | 0 | 0 | 38 | 290
4 | Location Management Service | 153 | 63 | 20 | 0 | 0 | 38 | 274
5 | Access Data Service | 130 | 10 | 7 | 0 | 0 | 39 | 186
6 | API Gateway (Azure APIM) | 84 | 0 | 0 | 7 | 0 | 57 | 148
7 | Notification Service | 190 | 8 | 0 | 8 | 10 | 72 | 288
8 | Help & Feedback Service | 108 | 16 | 0 | 16 | 17 | 39 | 196
9 | Integration Gateway | 150 | 20 | 0 | 0 | 0 | 66 | 236
10 | Search Indexing Pipeline | 84 | 22 | 10 | 0 | 0 | 39 | 155
11 | Lightweight Reporting (ADX + Power BI) | 54 | 15 | 4 | 11 | 0 | 40 | 124
12 | Resilience & DR | 174 | 60 | 68 | 0 | 0 | 204 | 506
| Subtotal by dev | 1611 | 323 | 149 | 118 | 254 | 710
15% | VAC&SICK | 242 | 49 | 23 | 18 | 39 | 107
10% | Team Communication | 162 | 33 | 15 | 12 | 26 | 71
5% | Code review/KT | 81 | 17 | 8 | 6 | 13 | 36
5% | Management | 81 | 17 | 8 | 6 | 13 | 36
| TOTAL by Dev | 2177 | 439 | 203 | 160 | 345 | 960 | 4284
20% | TOTAL QA | 436 | 88 | 41 | 32 | 69 | 192 | 858